## Product Backlog
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
R01 | User | Nhận được các thông báo, các cập nhật về xuất phim mới nhất | Tôi muốn nắm bắt được các bộ phim tôi yêu thích nhanh chóng để tự chủ thời gian xem phim. | 2 | Medium | - Tôi cần nhận được đặt lời nhắc gửi về tài khoản cho những phim sắp chiếu để mua vé và tranh những chỗ ngồi tôi muốn. | New
R02 | User | Đặt vé xem phim trên app qua ZaloPay, Momo | Tôi muốn được thanh toán online nhanh chóng mà không cần tiền mặt | 3 | High | - Tính năng đặt vé trực tuyến chỉ áp dụng cho thành viên đăng ký. - Khi tôi đặt vé tôi muốn được chọn rạp, chọn ghế theo ý mình nếu ghế trống. - Tôi sẽ nhận được mail và tin nhắn phản hồi khi đặt vé thành công - Khi xác nhận đặt vé, tôi có thể thanh toán bằng ZaloPay hay Momo nếu tài khoản ZaloPay hoặc Momo có đủ tiền và nhập đúng Pass - Nếu có vấn đề thanh toán, tôi muốn biết lí do và cách giải quyết - Tôi có thể hủy thanh toán bằng ZaloPay hay Momo | New
R03 | User | Có số Hotline, địa chỉ mail để liên hệ | Tôi muốn gọi cho Admin quản lí khi cần thiết và gửi được mail nếu cần chứng từ hình ảnh cho những vấn đề xảy ra. | 2 | Medium | - Sẽ có thanh hỗ trợ ở menu bên dưới màn hình chứa số điện thoại liên hệ và gmail. | New
R04 | User | Xem lịch sử đặt vé | Tôi muốn xem lại các vé mà tôi từng mua để xem lại thông tin vé lúc đó, thời gian mua, ghế ngồi,.. | 1 | Low | - Có một mục riêng trên menu để xem lại được lịch sử vé - Chứa thông tin lưu trữ của vé | New
R05 | User | Có thông tin phim cụ thể | Tôi muốn được các thông tin sơ bộ của phim, xem qua trailer phim, cut ngắn của phim để quyết định đến việc đặt vé phim đó | 1 | Low | - Khi nhấp vào một phim nó sẽ hiện được tên phim, hình ảnh , trailer, review sơ bộ của phim, đạo diễn,… | New
R06 | User | Thanh tìm kiếm | Tôi có chỗ để nhập tên phim và lọc thể loại phim | 2 | Medium | - Có thanh nhập được tên phim - Có thanh menu cạnh thanh tìm kiếm có chức năng lọc phim theo thể loại,… | New
R07 | Admin | Thống kê điểm thưởng | Tôi sẽ quy được điểm của từng tài khoản và áp vào các ưu đãi cho khách hàng mua vé. | 2 | Medium | - Nếu đặt phim trong tuần đầu ra mắt cộng 5 điểm - Nếu đặt phim trong 1 tháng đầu cộng 3 điểm - Những khách đặt phim công chiếu sau 1 tháng cộng 1 điểm ==>từ đó admin sẽ thống kê ra điểm thưởng của mỗi User để đưa ra chương trình khuyến mãi là 100 điểm đổi 1 vé xem miễn phí | New
R08 | Admin | Quản lý doanh thu | Để tôi nắm bắt doanh thu (ngày, tháng, năm) và số lượng vé tiêu thụ của từng phim. | 3 | High | - Có bảng thống kê Excel doanh thu theo ngày, tháng, năm. - Có danh sách những phim công chiếu và số vé mà phim tiêu thụ được. | New
R09 | Admin | Tạo ra các chương trình khuyến mãi. | Tôi muốn thu hút khách hàng, thông qua các chương trình giảm giá. | 2 | Medium | - Tôi định hướng sẽ tạo coupon giảm giá 30% vào thứ hai cuối tháng cùng các combo vé nếu mua kèm bắp, nước sẽ được giảm 20% - Tôi sẽ tạo các coupon đặc biệt sẽ rãi rác trong tháng giới hạn số lượng để thu hút khách hàng nhiều hơn. | New
R10 | Admin | Quản lí số lượng vé | Tôi muốn có thể đóng lại được chức năng mua vé, và quản lí số vé tối đa mà 1 tài khoản có thể đặt. | 2 | Medium | - Tôi sẽ đóng chức năng mua vé trực tuyến là 30 phút trước giờ chiếu phim hoặc khi suất chiếu đã được bán hết vé. - Tôi sẽ đặt yêu cầu số vé tối đa cho 1 khách hàng có thể đặt chỗ cho tối đa 8 khách (không bao gồm vé trẻ em) trong mỗi lần thực hiện. | New
R11 | Admin | Quản lí thông tin tài khoản đăng ký. | Tôi cần kiểm soát được mọi thông tin về tài khoản của khách hàng đã đăng ký trên phần mềm. | 3 | High | - Khi có một khách hàng tạo tài khoản thành công sẽ nhận được thông báo. - Tôi sẽ nhận được mọi thông tin mà khách hàng đã nhập. | New
R12 | Admin | Thêm, Sửa, Xóa phim. | Tôi muốn cập nhật liên tục các phim mới, chỉnh sữa khi có sai xót và xóa những phim ngừng công chiếu. | 3 | High | - Tạo hệ thống quản lí riêng cho Admin truy cập vào phần mềm. - Lọc danh sách các phim đã công chiếu, sắp công chiếu. - thống kê theo thời gian để xóa các phim sắp ngưng công chiếu. | New

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.